## Summary
| Priority | Initial Estimate | Actual Time Spent | Work Hours Left | Progress
Project 1 | High | 77 | 26.5 | 0 | 45.45%
Total |  | 77 | 26.5 | 0 | 100%
Total (+ Extra) |  | 77 | 26.5 | 0 | 100%
Timeframe
Start Date | Deadline | Work Days Left | Weekend Days Left | Total Days Left
2022-12-16 | 2023-01-31 | 20 | 7.7419 | 27.7419
Statistics
Estimated Velocity | Actual Velocity | Velocity needed for deadline | Current Velocity
1.6 h/day | 0.6 h/day | 0 h/day | 1.3 h/day
Formulas:
Initial Estimate = MAX(0,([Priority]-TODAY()+1)/7*5)

## Project 1 - dotnet project
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Section 1 | 3.5 | 2.5 | 0 | Done
Section 2 | 3.5 | 3.5 | 0 | Done
Section 3 | 3.5 | 2.5 |  | Done
Section 4 | 3.5 | 2.5 |  | Done
Section 5 | 3.5 | 2.5 |  | Done
Section 6 | 3.5 | 2.5 |  | Done
Section 7 | 3.5 | 2.5 |  | Done
Section 8 | 3.5 | 2.5 |  | Done
Section 9 | 3.5 | 2.5 |  | Done
Section 10 | 3.5 | 3 |  | Done
Section 11 | 3.5 |  |  | Not Started
Section 12 | 3.5 |  |  | Not Started
Section 13 | 3.5 |  |  | Not Started
Section 14 | 3.5 |  |  | Not Started
Section 15 | 3.5 |  |  | Not Started
Section 16 | 3.5 |  |  | Not Started
Section 17 | 3.5 |  |  | Not Started
Section 18 | 3.5 |  |  | Not Started
Section 19 | 3.5 |  |  | Not Started
Section 20 | 3.5 |  |  | Not Started
Section 21 | 3.5 |  |  | Not Started
Section 22 | 3.5 |  |  | Not Started

## Gotchas
When you duplicate a tab, all named ranges will automatically be duplicated as well with name SHEET!ORIGINAL_NAME. In most cases, this is fine and there is nothing explicit you should change in that sheet. What you have to update, though, is the project row in the "Summary" sheet. Use some of the others as reference what to put there.
Renaming a sheet will not break your statistics in the "Summary " sheet.
There is a hidden column D in all your project tabs. It contains some numbers which are used to calcuate remaining and current velocity. Make sure the formulas in those columns are not broken, otherwise your stats will be incorrect.